| Knowledge and understanding Action Plan 2016/2017 Curriculum Team: Lisa Wilcox Rebecca Woodward Rebecca Williams Ceri Bloom Heather Hewlett Kelda Remington |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Actions | Who Lead/ Support | Resources (Human, time and physical) | Budget | When? | Success Criteria |
| Audit of Science , History and Geography resources | L Wilcox R Williams | 1 day supply cover | 1 day supply cover | Autumn 1 2016 | Updated list of Science Resources given to staff. List of resources need for curriculum coverage produced. |
| Monitoring of standards in Science Levels 2 and 3 in Key Stage 2. | L Wilcox R Woodward. R Williams | 1 day supply cover | 1 day supply cover | Autumn 2 2016 | Monitoring of pupils work will show progression and accurate assessments of levels. Update portfolio of work. |
| Monitoring of standards in History and Geography levels 2,3 and 4. | L Wilcox | 1 day |  | Autumn 2 2016 | Monitoring of pupils work will show progression and accurate assessments of levels. Update portfolio of work. |
| Monitoring of standards in knowledge and understanding outcomes 2,3, 4, 5 and 6. | R Woodward | 1 day |  | Autumn 2 2016 | Monitoring of pupils work will show progression and accurate assessments of outcomes. Update portfolio of work. |
| Monitoring of scientific investigation skills | L Wilcox | Photocopy and laminate prompt sheets. | Photocopy sheets | Autumn 2 2106 | Prompt sheets displayed in learning environments and available for the children to use to complete work. |
| Ensure ICT is being used in Science, history and Geography topics in KS2 and in foundation phase. | All staff | Photocopy evidence of ICT being used. | Photocopying | Termly | Termly planning overview collected and collated illustrating coverage of ICT skill used in Science, History geography and knowledge. |
| Actions | Who Lead/ Support | Resources (Human, time and physical) | Budget | When? | Success Criteria |
| Knowledge and understanding team leader to attend Science course to implement new Karen Mills SOW. | L Wilcox | 1 day | 1 day supply Course cost £225 | July 2016 | Course attended and SOW implemented through KS2. Staff fully supported in delivery of SOW from team leader. |
| Long term plan of topics covered in Science SOW. | L Wilcox | Tuesday evening July |  | July 2016 | All staff aware of topics to be covered for their year group commencing the academic year 2017. |
| Knowledge and understanding leader to disseminate new SOW for Science in KS2 to staff during Inset session.. | L Wilcox | Inset session | Course cost | Autumn 1 2016 | Staff will be fully supported in the delivery and implementation of the new SOW. |
| Knowledge and understanding team to listen to learners views in Science and knowledge and understanding in foundation phase. | L Wilcox R Woodward R Williams | 1 day Listening to learners questionnaire | 1 supply day | Autumn 2 | Analysis of pupil s responses will give action points for improvements and ways forward for science and reflect the pupils understanding of what they are learning. |
| Staff questionnaire for new SOW for Science. | L Wilcox R Woodward R Williams | Questionnaire and time to complete | Photocopying | Spring 1 2017 | Analysis of questionnaire will inform team of any improvements that have been made and any support staff any need to implement the SOW. |
| Invite teaching and learning governor to school to discuss changes to the Science curriculum. | L Wilcox John Dyer | 1 hour | None | Spring 2 2017 | Teaching and learning governor fully aware of changes to the Science curriculum. Development of knowledge of Science . |
| Actions | Who Lead/ Support | Resources (Human, time and physical) | Budget | When? | Success Criteria |
| To continue with Eco club to maintain the Silver flag award. | R Williams K Rennington | Time for eco meetings | £100 | Lunchtimes | Eco children will be voted in by a ballot and attend regular meetings where they will have an input on school issues regarding transport, outdoor environment, litter, energy, water, healthy eating and global citizenship. |
| To write an Eco-action plan for 2016/2017 outlining the suggestions the Eco Assessor advised. | L Wilcox R Williams K Rennington | Time to write action plan. | None | After school | Eco Club will have a separate action plan where they will be able to focus on the actions to be awarded/ maintain the silver flag status. |
| At the beginning of the academic year staff set targets for individual pupils for Science at KS2 to make 2 sub levels progress. | R Woodward | Inset Time | None | Sept 2016 | Increase level 4 and 5 science results through identifying individual pupils and monitoring progress and attainment. |
| Pupil progress meetings to include discussion about attainment and progress in Science at KS2. | R Woodward | Supply cover for all KS2 teaching staff. | Supply costs | ½ termly | Through progress meetings individual pupils are tracked and most pupils will make 2 sub levels progress in a year. |