| KEY PRIORITY – Nurture Article 18 – Parental responsibilities Article 28 – Right to Education Article 29 – Goals of Education Goal: All pupils will learn in a nurturing environment to support good progress in their learning. Rationale: Strong nurture values are essential at Meadowlane as our pupils require a supportive and nurturing environment to enable them to make progress. A consistent approach across the school is needed to enable pupils to feel safe and secure. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Success Criteria: - Nearly all staff will use nurturing language. - Most staff will follow restorative approaches as described in our Relationships Policy. - Most pupils make progress in their personal development, demonstrated through their Boxall profile. |  |  |  |  |  | Autumn; Spring; Summer. |
| Leaders: Tom Simmonds |  |  |  |  |  |  |  |
| Actions | Personnel Involved | Budget / Resources (Human, time and physical) | Timescales | Self-Evaluation Activities | Self-Evaluation |  | Evidence |
| - All staff to use nurturing language; reminders to be given through briefing and staff training sessions. | All staff | Meetings | Ongoing throughout the year | Pupil discussions Learning walk |  |  |  |
| - New staff to meet with TS for nurturing language introduction. | TS | N/A | As required | Pupil discussions Learning walk |  |  |  |
| - Nurture board for staff to support work by staff room | TS & LIM | N/A | By October 2023 | Display |  |  |  |
| - Boxall profiles completed twice a year to track and identify barriers to learning and common trends. Teachers to implement strategies to address barriers. | Teachers | Teaching time | January and July | Boxall data |  |  | Boxall data |
| - Whole class strategies to be shared with all staff. | TS | INSET | 4/9/23 | Boxall data |  |  |  |
| - All staff to use whole class strategies to help build positive relationships in class. | Teachers | N/A | Ongoing throughout the year | Pupil discussions Behaviour records – Provision Maps |  |  |  |
| - Jane Miles to deliver whole staff training on positive relationship building and using effective nurturing language. | BW to organise. All teaching staff to attend. TAs to be invited. | N/A | TBC | Pupil discussions Learning Walks |  |  |  |
| - School to work towards whole school Nurturing International award. | TS | Teaching time | Ongoing throughout the year | Nurturing International Award self-assessment Case studies Boxall data Classroom environments Dosbarth Wye |  |  |  |
| - Dosbarth Wye specialist provision classroom to support identified pupils in meeting their individual needs. Article 28 – Right to an education. | HE/BW | N/A | September/October 2022 | Learning walk Pupil discussions Progress data analysis |  |  |  |
| - All teaching staff to use daily greeting to check in with children at the beginning of the day and after lunch. Check in options to be used. | Teachers | N/A | Ongoing throughout the year | Discussions with pupils |  |  |  |
| - Circles to be completed by class teacher every Monday or Tuesday following the developed circles programme. | Class teachers | N/A | Weekly | Discussions with pupils |  |  |  |
| - Restorative behaviour steps to be followed by all staff. | All staff | INSET | 4/9/23 |  |  |  |  |
| - Restorative approaches to be used by all staff. | All staff | INSET | 4/9/23 |  |  |  |  |
| - Supply teachers to be provided with lanyard and restorative question card. | TS, supported by AO | Photocopying cost Lanyard Purchase | Ongoing throughout the year | Pupil discussions |  |  |  |
| - Health and Well-being topic to be the first whole school topic; to include e-safety. | Teachers | N/A | Autumn 1 | Pupil discussions Dojo/ Twitter/ website |  |  |  |
| - Year 5 and 6 parents to be invited in for online safety guidance talk. | TS, LIM, MB | N/A | September 23 | Parent feedback Online incidents record – Provision Maps |  |  |  |
| - To maintain the Gold Rights Respecting school award. Article 42 – Knowledge of rights. | TS, supported by all staff |  | Ongoing throughout the year | Planning to show Rights Dojo/ Twitter and website Assembly overview Pupil discussions July 2024 – Gold award renewed |  |  |  |
| - To continue to develop the ‘i-voice’ to ensure pupils are actively involved in the life of the school and that pupils are involved in decision making to support school improvement. Article 12 – Respect the views of the child. Article 13 – freedom of expression. | Teachers |  | Ongoing throughout the year | I-Voice/ class team minutes I – voice displays Pupil discussions Group assemblies |  |  |  |
| 19. Nurture buddies in Dosbarth Rhymney to work with Year 1 and 2 to support their well-being. | JM/LW JSM/LM/SR | N/A | From Autumn 2 | Pupil discussions |  |  |  |
| 20. SLT to evaluate staff training needs throughout the year, and plan for these. | CF supported by JR | £14000 PL Grant and Collaboration Grant to support | Half termly | Self-Evaluation activities |  |  |  |