| SCHOOL KEY PRIORITY ONE: Improve attendance Target 95% |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Actions | Who Lead/ Support | Resources (Human, time and physical) | Budget | When? | Success Criteria |
| - Regularly share timings for the start of the day with parents, through newsletters, SCHOOP and the website. | Chloe Langson | Admin staff Gemma Price | PDG: Schoop £838.80 Website £419 FEO staffing cost | From September 2016 | By July 2017 less than 1.5% children will arrive in school late, after 8.55am. |
| - Family engagement officer to meet with parents of children who are persistently late to offer support. | Jo Wood | Gemma Price | PDG: FEO | From September 2016 | By July 2017 less than 1.5% children will arrive in school late, after 8.55am. |
| - Parents of children who are late (after 9.25am) more than ten times to be fined. | Chloe Langson/ Jo Wood | Admin time EWO involvement | 0 | From Sept 16 | By July 2017 less than 1.5% children will arrive in school late, after 8.55am. By July 2017 attendance will be 95%. |
| - 100% attendance awards to be presented at the end of each term. Children rewarded. Attendance trip. | Chloe Langson | Admin time | PDG £1600 | 11/1/17 2/5/17 18/7/17 | By January 2017, the number of children attending the 100% attendance trip will be in excess of 45. By May 2017, the number of children attending the 100% attendance trip will be in excess of 84. By July 2017, the number of children attending the 100% attendance trip will be in excess of 43. |
| - Reward parents for improved attendance | Jo Wood Gemma Price | Admin time FEO | PDG £1600 (inc. above) | December 2016 April 2017 July 2017 | By January 2016, the parents of the top 5 most improved attendance children will have received rewards. By, April 2017, a further 5 parents of the top most improved attendance children will have received rewards. By July 2017, a further 5 parents of the top most improved attendance children will have received rewards. By July 2017, attendance will be 95%. |
| - Fortnightly newsletter to update parents on class attendance – shared through SCHOOP and website. | Jo Wood | Admin time | PDG: Schoop, website | Throughout the year | By July 2017 attendance will be 95%. |
| - Weekly class attendance award in school celebration assembly. | Chloe Langson |  | 0 | Throughout the year | By July 2017 attendance will be 95%. |
| - Hands on learning experiences to be planned regularly for the children to engage, inspire and motivate the children in their learning. | Jane Milner | Class teachers | PDG £5000 experiences and opportunities | Throughout the year | By February 2017 children want to be in school and talk positively about their school experiences. By July 2017 attendance is 95%. |
| - Letters to be sent every half term to any families where attendance has dropped below 90%. | Jo Wood | Attendance Officer Support | 0 | October 2016 December 2016 February 2017 March 2017 July 2017 | By March 2017 the percentage of children with attendance below 85% will be below 1.5% By July 2017 the percentage of children with attendance below 85% will be less than 1% |
| - Family Engagement Officer to work with families of children who are persistently absent (attendance below 85%) | Jo Wood | Gemma Price Attendance support officer EWO | 0 | Throughout the year | By March 2017 the percentage of children with attendance below 85% will be below 1.5% By July 2017 the percentage of children with attendance below 85% will be less than 1% |
| - Parents of persistent absentees to provide evidence of all absences. | Jo Wood |  | 0 | Throughout the year | By March 2017 the percentage of children with attendance below 85% will be below 1.5% By July 2017 the percentage of children with attendance below 85% will be less than 1% |
| - Parents of children who have more than 10 sessions of unauthorised absence to be fined. | Jo Wood | EWO involvement | 0 | Throughout the year | By July 2017 attendance will be 95% |
| - Family engagement officer to work closely with parents of persistent absentees to provide support and ensure attendance to school. Daily phone calls to parents before from 8.15am until 8.45am and house calls from 8.45am until 9.30am. Further phone calls to be made between 11.30am and 12pm. | Gemma Price |  | Mobile Phone cost £** | Throughout the year | By July 2016 attendance will be 95% |
| - Create a welcoming Entrance Area to the school. | Gemma Price | Chloe Langson Estate Manager | £1000 PDG | January 2016 | By March 2017, parents will feel comfortable coming into school, due to an inviting and comfortable entrance area. By July 20167 parents will report that they feel comfortable coming into school; this will lead to further parental support with children’s learning |
| - Engage with parents of those children whose attendance is below 85%, through a variety of workshops, to give them a more positive attitude about school. | Gemma Price | Communities First |  | Monday afternoons | By July 2017, attendance will be 95%. |
| 16. After two unauthorised absences, a letter sent home to make the parent aware of the consequences of further unauthorised absences. | Jo Wood | Admin time |  | Throughout the year | By January 2017, the number of unauthorised absences will reduce to 2.8%. By July 2017, the number of unauthorised absences will reduce to 2%. |
| 17. After 5 unauthorised absences a letter is sent home to make the parent aware of the consequences of further unauthorised absences. | Jo Wood | Admin time |  | Throughout the year | By January 2017, the number of unauthorised absences will reduce to 2.8%. By July 2017, the number of unauthorised absences will reduce to 2%. |
| 18. After 5 unauthorised absences, a meeting is arranged with the FEO to discuss problems and offer support. | Jo Wood Gemma Price | Admin time FEO time |  | Throughout the year | By January 2017, the number of unauthorised absences will reduce to 2.8%. By July 2017, the number of unauthorised absences will reduce to 2%. |
| 19. Every four weeks, a letter to be sent to all parents where attendance is below 95%. | Jo Wood | Admin time |  | Throughout the year, starting Monday 3rd October | By July 2017, attendance will be 95%. |
| 20. Each term, all parents with children who have attendance above 95% to be put in a raffle for an i-pod touch. | Jo Wood | Admin time | PDG £1600 (inc. above) | December 2016 April 2017 July 2017 | By July 2017, attendance will be 95%. |