| KEY PRIORITY 2 – Develop the new curriculum for Wales at Meadowlane Every child will receive great learning and teaching experiences that will allow them to develop in line with the Four Purposes of the New Curriculum for Wales. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale for priority The New Curriculum for Wales will become statutory in 2022, with the draft documentation now available we are able to further develop our curriculum at Meadowlane. This will take into account the needs and experiences of our pupils and provide engaging and enriching learning activities which will meet the Four Purposes of the new curriculum. Through a variety of contexts for learning pupils will have opportunities to apply their skills purposefully and extend their thinking. |  |  |  |  |  |  |  |
| Success Criteria: - All staff will be familiar with the new curriculum documentation and how it impacts on their teaching. - All learners will be able to apply their skills and extend their thinking through a range of contexts. - All teachers will be using the What Matters statements and the Experiences, Knowledge & Skills documents to plan and evaluate lessons. |  |  |  |  |  | Autumn; Spring; Summer. |
| Key Priority Leader: Jane Milner Team Members: |  |  |  |  |  |  |  |
| Actions | Personnel Involved | Budget / Resources (Human, time and physical) | Timescales | Self Evaluation Activities | Self-Evaluation |  | Evidence |
| 1.Whole school termly topics will be planned to include a WoW, and Marvellous Middle and a Celebration. | Teachers | INSETs | 2.9.19, 22.10.19, 26.11.19 Spring 2020, Summer 2020 | Analyse planning for each topic. Pupil Discussions. Wb 9.12.19, wb23.3.20 wb 8.6.20 |  |  |  |
| 2.Topics will focus on an AOLE but will include all other AOLEs in order to ensure a range of experiences for our learners (particularly boys) and will be learning-led rather than activity-led | Teachers |  | Dates as above and Wb 9.12.19, wb 23.3.20, wb 8.6.20 | Analyse Building blocks to check on coverage of AoLEs. Pupil discussion, book scrutiny and Learning walk Wb 9.12.19, wb 23.3.20, wb 8.6.20 |  |  |  |
| 3.Pupil voice will be used across the school to support teachers in planning opportunities where children can apply their skills purposefully. A particular focus on boys in the FP and more able boys in KS2. | Teachers |  | Wb 9.12.19, wb 23.3.20, wb 8.6.20 | Pupil discussions and learning walks Dates as above. |  |  |  |
| 4.Coverage of experiences, knowledge and skills will be tracked using the new Building Blocks. | All staff |  | Throughout the year | Analysis of Building Blocks Dates as above |  |  |  |
| 5.Individual research - ‘Passion Project’ to be included as part of PM and to cover an aspect of the New Curriculum. | All teachers | PM meetings 1 day per teacher covered by HLTA INSET | Autumn 2019 - cover October 2019 - meetings March 2020 – meetings July 2020 - INSET | Teacher presentations July 2020. |  |  |  |
| 6.The Four Purposes to be referred to after teacher led activities. | All staff |  | Throughout the year | In pupil discussions, nearly all children will be able talk about how their learning links to the FPs. Dates as previous. |  |  |  |
| 7. All teaching staff at MLPS will have been involved in reviewing, analysing and deciding upon ways forward to take the new curriculum. | All staff. JM, JR lead. | Twilight INSET | 22.10.19 26.11.19 3.12.19 10.12.19 | Review of staff evaluations |  |  |  |
| 8. Nearly all learners will be familiar with the language of the new curriculum. | All staff | Time given to all staff members to record range of learners discussing aspects of the new curriculum. | Wb 9.12.19, Wb23.3.20 Wb 8.6.20 | Pupil discussions and Lesson observations |  |  |  |
| 9. All phases will be involved in feeding back on their topics via assemblies, class feedback sessions via newsletters/ letters to pupils and parents, twitter and the school website | All classes/ pupils | Time given towards end of topics to plan method of feedback and allow pupils to practice their findings ready for presenting. | By Dec 19 all classes will be involved in feeding back to given audience. By March 20, all learners will present topic findings using a different approach. By July 20 all learners will plan and deliver their topic findings using preferred method. | Video evidence. L2L about feedback methods. Review what went well/ didn’t. |  |  |  |
| 10. SLT will begin to develop procedures to assess learners against the Progression Steps of the new curriculum. | SLT | SLT meetings | Throughout the year | SLT meetings minutes |  |  |  |
| 11. Oracy to be a key priority within new curriculum planning; children to develop a range of oracy skills. | Literacy Leaders Teachers | INSETs | 22/10/19 January 2020 April 2020 July 2020 | Oracy data analysis Scrutiny of oracy evidence |  |  |  |
| 12.Governors to support in evaluating the new curriculum | Governors | Monitoring weeks Governors meetings | WB 14/10/19 WB 25/11/19 WB 27/1/20 WB 23/3/20 | Governors reports Governors minutes of meetings |  |  |  |
| 13. Many teachers to have the opportunity to work alongside colleagues from Cluster and SIG schools to share good practice. | Teachers | Time to be covered by HLTAs | Dates to be confirmed | Curriculum evaluations/ reviews |  |  |  |
| 14. Curriculum Leader to work with Cluster Schools sharing effective practice. | Curriculum leader | Half termly meetings | November 2019 February 2010 May 2020 July 2020 | Curriculum evaluations/ reviews |  |  |  |
| 15. Key Stage 2 to increase use of the outdoor environment to enhance their curriculum. | KS2 teachers |  | Wb 9.12.19, wb 23.3.20, wb 8.6.20 | Analysis of planning Pupil discussions |  |  |  |