| KEY PRIORITY THREE: To further raise standards in Maths End of Foundation Phase: 90% Outcome 5+ and 28% Outcome 6 End of Key Stage 2: 89 Level 4+, 34% Level 5+ and 9% Level 6 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Actions | Who Lead/ Support | Resources (Human, time and physical) | Budget | When? | Success Criteria |
| 1. Half termly pupil progress meetings to take place focusing on tracking data and teacher assessments. Pupils underachieving to be identified and support discussed and agreed. | R Woodward H marsh Staff | Assessment leader ALNCO Class teachers Pupil progress meetings x5 | PDG: £1875 15 days supply | Every half term | By November 2016 children not on track to meet their individual targets are identified based on teacher assessment. Interventions and support discussed and put in place. By January 2017 intervention and support shows improved progress or attainment. By March 2017 interventions or support shows progress or attainment improvements. |
| 2. Pupils not on track to meet their targets will receive interventions either within class support or in small groups. | Hannah Marsh | Teachers support staff | Grade 4 TAs within PDG staffing | Every half term | By November 2016 support staff and teachers to support children at risk of not making progress. By July 2017 children to meet their end of year target. |
| 3. Moderation of maths outcomes and levels to take place regularly. | Kate Stork Jane Milner | Class teachers Staff inset x3 |  | Autumn 16 Spring 17 Summer 17 | By June 2017 teacher assessments verified and accurate. |
| 4. SLT to monitor quality of teaching in maths through book scrutiny, lesson observations, learning walks and pupil discussions. | Chloe Langson Supported by SLT | Once a term Random checks by maths leaders | 2 ½ day supply £315 |  | By January 2016 any areas for development are addressed by all. By June 2017 100% of the teaching of maths judged as at least good. By July 2017, maths books will show good progress by nearly all pupils. |
| 5. Daily maths to take place in both Foundation Phase and Key Stage 2. | Kate Stork Jane Milner | Teachers Monitoring time for maths leaders | 2 days supply £250 | From September 2016 | By October 2016 children’s maths books show daily maths activities and opportunities. By March 2017 children’s books to show increased daily maths opportunities. By July 2017, there are clear daily maths opportunities within all books. |
| 6. Attend SIG meetings to share good practice in mathematical development and maths. | Chloe Langson Rebecca Woodward | Maths Leaders time | SIG funds | Dates to be arranged | By April 2017, relevant changes to practice will be have been made and evidenced through planning and children’s work. |
| 7. Analysis of the national test procedural and numerical reasoning data to look for areas to improve or develop. | Jane Milner Kate Stork Rebecca Woodward | 1 day for analysis | 2 days supply £250 | September | By September 2016, data has been analysed. By October 2016, steps have been taken to develop any areas of concern. |
| 8. Whole school wall paper activity to be carried out to identify strengths and weakness in maths across the school. | Kate Stork Jane Milner | Class teachers Inset | 0 | 22/11/16 March 2017 June 2017 | By November 2016, whole school strengths and areas to be developed are identified. By March 2017, progress of identified areas is evident and new areas to be developed are identified. By July 2017, all identified areas for development have been addressed as evident in children’s books and teacher planning. |
| 9. More able pupils to be given additional challenges in class. | Kate Stork Jane Milner |  |  |  | By October 2016, teacher planning will clearly show challenge for the more able. By February 2017, there will be clear challenge shown in children’s books and children will talk about feeling challenged within their lessons. By July 2017, **% FP children will achieve Outcome 6 and **% of Year 6 children will achieve Level 5 and *% Level 6. |
| 10. Develop the use of Success Criteria in Maths, ensuring it is differentiated appropriately. | Kate Stork Jane Milner | INSET – wall paper activity |  | 22/11/16 Spring 2017 Summer 2017 | By November 2016, success criteria will be evident in children’s books. By April 2017, all children are using differentiated success criteria to support them in their Maths progress. By July 2017, pupils will be suggesting their own Success Criteria for their work. |
| 11. Abacus active learn refresher sessions. | Kate Stork Jane Milner | Afternoon time | 5 days supply £625 CPD | September 2016 | By October 2016, all staff will be confident in the use of Abacus Active Learn. By February 2017, there will be consistency in the teaching of Maths and children will be making good progress towards their targets. |
| 12. Scrutiny of maths planning to ensure differentiation and coverage, progression and daily adaptation to meet needs of learners. | Kate Stork Jane Milner SLT | Half day non-contact x2 | £ 250 | Autumn 2 | By December 2016, planning will show differentiation, coverage and progression to meet the needs of individual learners. Planning will be evaluated and lead to ways forward in short term planning. |
| 13. Ensure all staff have received Big Maths Training. | Kate Stork Jane Milner | KM, new staff including TAs | £150 X3 = £450 Supply £375 CPD |  | By December 2016, all staff will be confident using the program in their class. Evidence of this will be through classroom observations and pupil interviews. |
| 14. Moderation of INCERTS against evidence in books. | Kate Stork Jane Milner RW | 2x one day non contact | £250 | Summer 1 2017 | By June 2017, work in books and pupil targets will be accurately matched to INCERTS data. |
| 15. Develop learner profile for each level/Outcome. | Kate Stork Jane Milner | Directed time |  | On going from Summer 2016 | By July 2017, learner profiles for each level/Outcome will be retained and disseminated to staff as a point of reference and confirmation of levels/Outcomes. |
| 16. Introduce Building Blocks across the school to develop application of numeracy. | JSM SLT | WS training session Summer 2016 | Building Blocks £3000 | Autumn 1 | By March 2017, at least half the Numeracy skills from the LNF will have been used by the children in different contexts. By July 2017, children will have used all the necessary maths skills within a variety of contexts. |