| KEY PRIORITY: Assessment and Progression Article 29 – Education must develop every child’s personality, talents and abilities Goal: Pupils are at the heart of assessment processes, and as a result, most pupils make appropriate progress or better in their learning Rationale: This is a priority at Meadowlane due to the changes in assessment processes as part of the new curriculum. Robust assessment procedures are needed to effectively support all children in making progress. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Success Criteria: - Most pupils make appropriate progress in their learning - Nearly all teachers are familiar with the expectations within each Progression Step and use this to support pupils in making progress - Most pupils can talk about their learning and progress with confidence |  |  |  |  | Autumn; Spring; Summer. |
| Leaders: Chloe Ford |  |  |  |  |  |  |
| Actions | Personnel Involved | Budget / Resources (Human, time and physical) | Timescales | Self Evaluation Activities | Self-Evaluation | Evidence |
| - Assessments to be carried out throughout the year in line with the assessment overview. (Appendix 1). All data to be analysed to identify strengths and areas of concern. | CF, supported by SLT | Staff INSETs – wall paper activities Teachers to carry out assessments Head & Deputy to analyse progress | 17/10/23 21/11/23 Spring & Summer dates TBC From November onwards | Analysis of assessment data Wall paper activities |  |  |
| - Ensure there is consistency with all data collected and formal assessments carried out through: - Internal Professional Dialogues (PDs) - Cluster PDs - Wall paper activities | CF, supported by SLT | Wall paper INSETs Cluster INSETs Internal professional Dialogues (£1560 PL Grant) | 17/10/23 21/11/23 3/10/23 14/11/23 Spring and Summer dates TBC 24th/26th Oct 30th Jan/ 1st Feb 30th April/ 1st May 2nd/4th July | - Scrutiny of pupils books/ discussions with pupils - Analysis of data - Wall paper activities - Professional dialogues |  |  |
| - On entry assessments for Nursery and Reception (and any new child arriving into FL) to be utilised in assessing all areas important for our Meadowlane pupils. These will be assessed against, from N – Year 2 | JSM All N-Y2 staff | N/A | Ongoing | Pupil profiles Pupil discussions Data analysis |  |  |
| - All pupils to receive effective feedback; verbal and written, to support their progress. Ensure this is developed further in FL classes in line with the FL pedagogy. | Teachers | Wall paper INSETs Professional dialogues INSETs | 17/10/23 21/11/23 Spring and summer TBC 24th/26th Oct 30th Jan/ 1st Feb 30th April/ 1st May 2nd/4th July 29/10/23 10/10/23 | Pupil discussions with books Learning Walks Progress data |  |  |
| - Success Criteria to be available in all lessons for pupils to assess against. Pupils to contribute to/ write their SC, dependent on age and context. | Teachers | Self-evaluation days – Head, SLT, Teacher, TA + ANOther (PDG £1000) | Ongoing throughout year | Pupil discussions Learning Walks |  |  |
| - Self-assessment to be integral to all lessons to support pupils in identifying their strengths and areas for development. Regular ‘Pit stops’ to be used to enable this. | Teachers | Self-evaluation days – Head, SLT, Teacher, TA + ANOther | Ongoing throughout the year | Pupil discussions and book scrutiny Learning Walks |  |  |
| - Peer-assessment to be used regularly to support pupil’s progress; regular ‘Pit stops’ to be used to enable this. | Teachers | Self-evaluation days – Head, SLT, Teacher, TA + ANOther | Ongoing throughout the year | Pupil discussions and book scrutiny Learning Walks |  |  |
| - Pupils to continue to have a metacognition target each half term and will assess their current position on their metacognition progression maps then devise and share a strategy to meet their next steps. | JSM supported by metacognition team | Meta-cognition Team meetings X4 teacher & x2 TAs supply £1030 x 6 = £6180 PDG Metacognition reviews – teacher release £5000 (PDG) Self evaluations days – JM, RW, Teacher and TA (£1000 PDG) | Autumn 1 Autumn 2 Spring 1, Spring 2 Summer 1, Summer 2 | Pupil discussions Learning Environments Pupil Progress files |  |  |
| - Nick Jones- ‘Excellent Teaching Course’ to explore strategies for excellent teaching to enable our pupils to make excellent progress in their learning. Actions from the day to be added to the SDP. | CF | INSET Day £1800 PL Grant Twilight INSET | 29/9/23 10/10/23 | Self evaluation days: Learning walks Pupil discussions with books |  |  |
| - Termly professional dialogues to take place regarding pupils who are making limited or no progress, and children making exceptional progress; teachers to make changes to own practice to support this. Ensure our more able Meadowlane learners are included. | CF & RW | Internal cover x8 days | 24th/26th Oct 30th Jan/ 1st Feb 30th April/ 1st May 2nd/4th July | Professional dialogues with teachers: Teacher proforma identifying children making limited progress, expected and exceeding, with barriers and strategies Book scrutiny Data analysis |  |  |
| - Ensure all staff have professional dialogue opportunities to understand what pupil progress looks like in each of the AoLE, using the Cluster progression maps. | AoLE Leads | H&W INSET AoLE Leaders INSET Humanities INSET Sci&Tech INSET Expressive arts INSET | 5/9/23 19/9/23 24/10/23 12/12/23 Spring Term | Analysis of Pupil learning: Work scrutiny Pupils discussions Placemats |  |  |
| - Professional Dialogues about learning in Writing and Maths progress to take place using a wall paper activity. | JR and JSM | INSETs | 17/10/23 21/11/23 X2 Spring Term X2 Summer term | INSET minutes |  |  |
| - Ensure clear understanding of what ‘Expected progress’ looks like and what ‘Good progress’ looks like. | CF | INSETs | Spring Term Summer Term | Professional dialogues with teachers Progress Data analysis Book scrutiny |  |  |
| - Assessment Leaders across the cluster to share good practice and agree on consistent approaches in identified areas. | CF | X6 days | 5/10/23 16/11/23 25/1/24 14/3/24 25/4/24 20/6/24 | Data analysis Tracking system |  |  |
| - Pupils to record all they know about a topic at the beginning, so they can add all their new knowledge and skills by the end of the topic – to be displayed in class to be referred to, enabling children to talk about their progress and learning journey | Class teachers |  | Beginning and end of every new topic | Pupil discussions Learning walks Learning environment displays |  |  |
| - Class placemats/ floor books to be created at the end of every topic covering: Literacy, numeracy and digital skills used and applied, welsh learnt, topic learning, experiences, Four Purposes worked on. These can be used to see progression across the school, and for children to review their own learning. | Class teachers |  | At the end of every topic | Placemats Pupil discussions |  |  |
| 17. SLT to evaluate staff training needs throughout the year, and plan for these. | CF supported by JR | £14000 PL Grant and Collaboration Grant to support | Half termly | Self-Evaluation activities |  |  |