| SCHOOL KEY PRIORITY FOUR: Improve attendance Target 95% |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Actions | Who Lead/ Support | Resources (Human, time and physical) | Budget | When? | Success Criteria |
| - Regularly share timings for the start of the day with parents, through newsletters, SCHOOP and the website. | Chloe Langson | Admin staff Gemma Price | PDG: Schoop, Website, FEO | From September 2015 | By July 2016 fewer children will arrive in school late, after 8.55am. |
| - Family engagement officer to meet with parents of children who are persistently late to offer support. | Chloe Langson supported by Jo Wood | Gemma Price | PDG: FEO | From September 2015 | By July 2016 fewer children will arrive in school late, after 8.55am. |
| - Parents of children who are late (after 9.25am) more than ten times to be fined. | Chloe Langson/ Jo Wood | Admin time EWO involvement | 0 | From Sept 16 | By July 2016 fewer children will arrive in school late, after 8.55am. By July 2015 attendance will be 95%. |
| - 100% attendance awards to be presented at the end of each term. Children rewarded. Attendance trip. | Chloe Langson | Admin time | £1000 PDG | 19/1/16 26/4/16 19/7/16 | By March 2016 the percentage of children with attendance below 85% will be below 8%. By July 2016 the percentage of children with attendance below 85% will have dropped to 5%. |
| - Fortnightly newsletter to update parents on class attendance – shared through SCHOOP and website. | Jo Wood | Admin time | PDG: Schoop, website | Throughout the year | By July 2015 attendance will be 95%. |
| - Weekly class attendance award in school celebration assembly. | Chloe Langson |  | 0 | Throughout the year | By July 2015 attendance will be 95%. |
| - Hands on learning experiences to be planned regularly for the children to engage, inspire and motivate the children in their learning. | Jane Milner | Class teachers | From £9900 PDG experiences and opportunities | Throughout the year | By February 2016 children want to be in school and talk positively about their school experiences. By July 2016 attendance is 95%. |
| - Letters to be sent every half term to any families where attendance has dropped below 90%. | Jo Wood Gemma Price | Attendance Officer Support | 0 | October 2015 December 2015 February 2016 March 2016 May 2016 July 2016 | By March 2016 the percentage of children with attendance below 85% will be below 8%. By July 2016 the percentage of children with attendance below 85% will have dropped to 5%. |
| - EWO/ Attendance Officer and family engagement officer to work with families of children who are persistently absent. | Chloe Langson | Jo Wood Gemma Price Attendance support officer EWO | 0 | Throughout the year | By March 2016 the percentage of children with attendance below 85% will be below 8%. By July 2016 the percentage of children with attendance below 85% will have dropped to 5%. |
| - Parents of persistent absentees to provide evidence of all absences. | Jo Wood |  | 0 | Throughout the year | By March 2016 the percentage of children with attendance below 85% will be below 8%. By July 2016 the percentage of children with attendance below 85% will have dropped to 5%. |
| - Parents of children who have more than 10 sessions of unauthorised absence to be fined. | Chloe Langson/Jo Wood | EWO involvement | 0 | September | By July 2016 attendance will be 95% |
| - Family engagement officer to work closely with parents of persistent absentees to provide support and ensure attendance to school. Daily phone calls to parents before 8.30 and house calls. | Gemma Price |  |  | Throughout the year | By July 2016 attendance will be 95% |
| - Daily after school clubs to be set up to actively encourage attendance for persistent absentees. | Becky Woodward | Gemma Price TAs Teachers | PDG: After School Clubs | Throughout the year | By July 2016 attendance will be 95% |
| - Introduce a compulsory school uniform to create positive attitudes towards school and learning for all. | Chloe Langson | All staff | £750 PDG | September 2015 | By October 2015 all children will be wearing correct school uniform, and through a sense of belonging will want to be in school each day. Attitudes to school and learning will be positive. |
| - Create a welcoming Entrance Area. To the school and to the nursery unit. | Gemma Price | Chloe Langson Estate Manager | £4000 PDG £2000 EY PDG | January 2016 | By March 2016, parents will feel comfortable coming into school, due to an inviting and comfortable entrance area. By July 2016, parents will report that they feel comfortable coming into school; this will lead to further parental support with children’s learning |