| KEY PRIORITY 4 – Leadership and Management |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Actions | Who Lead/ Support | Resources (Human, time and physical) | Budget | When? | Success Criteria |
| ENGLISH Aim: Ensure all teacher assessments are accurate. |  |  |  |  |  |
| - SLT to scrutinise the teacher assessments for accuracy and use outcomes to inform Key Stage INSETs. | RW supported by SJR | INCERTs Management time | £966 PDG Included within staffing structure | Nov 18, Feb 19, Jun 19 | By May 2019, cluster moderation will confirm the school’s teacher assessments. |
| - Regular Key Stage INSET will take place to explore learners writing, discussing overall sub levels/ outcomes. | JR/CT supported by teachers | INSET Attendance at Cluster moderation | £850 supply from main budget | Nov 18, Feb 19, May 19, Jun 19 | By December 2018, most writing assessments will be accurate due to teachers recognising aspects and differences in sub levels/outcomes in writing. By February 2019, nearly all writing assessments will be accurate. By May 2019, cluster moderation will confirm the school’s teacher assessments as accurate. By July 2019, all teacher assessments will be accurate. |
| - Writing wallpaper exercises will be undertaken termly to identify strengths and areas for improvement in aspects of writing/ marking/ moderation of levels. | JR | INSET | N/A | 3/9/18 20/11/18 Feb 19 Jun 19 | By September 2018, all teachers will understand areas that require improvement in writing and each Key Stage will have a plan to address these. By November 2018, the areas needing improvement from September 18 will have been addressed and further areas will be identified and planned for. To be repeated in February 2019 and June 2019. |
| - Introduce Salford Reading Tests to inform children’s reading ages. | JR supported by RW | N/A | £53 general school resources budget | October 2018 March 2019 July 2019 | By March 2019, SLT will be able to analyse reading progress across the school and will use this information to address areas in need of improvement. By July 2019, Governors will be fully informed of reading progress using Reading Ages. |
| WELSH Aims: Promote the use of the Welsh Language and culture across the school |  |  |  |  |  |
| - Ensure oracy evidence is collected at least 3 times per year on identified learners. 1 child per level/outcome. | LM supported by teachers | Meadow | N/A | Nov 18, Feb 19, Jun 19 | By November 2018, each class will have evidence from three children to support assessment of Welsh Oracy skills. By February 2019, each class will have further evidence of Welsh Oracy skills for the selected three children. By June 2019, there will be a good amount of wlesh oracy assessment evidence to support cluster moderation/ in house moderation purposes. |
| - To achieve the Bronze Cymraeg Campus award. | LM | INSET | N/A | 27/11/18 | By July 2019, Meadowlane will have received the Bronze Cymraeg Campus award. |
| - Survey learners using CC audit tool. (beginning/ end) | LM supported by teachers | Survey tool | N/A | October 2018 July 2019 | By July 2019, the percentage of children understanding the importance of being Welsh/ promoting bilingualism will have increased significantly from October 2018. |
| - Set targets in response to the audit tool. | LM | Audit survey tool | Supply costs x1 day | October 18 | By October 2018, all children will have completed the CC audit. An action plan will be written to further develop children’s perceptions/ understanding on their Welsh ness/ bilingualism. By July 2019, most actions from the CC plan will have been carried out effectively. |
| - Make reception area fully bilingual to show MLPS is a school in Wales that promotes bilingualism. | LM supported by AO | Display resources | N/A | Ongoing from September 2018 | By October 2018, the reception area will be fully bilingual and therefore visitors will know Meadowlane is a school that embraces the Welsh culture and language. |
| - Have prominent display in hall and key stage phases for current Bronze target being achieved. | LM suppprted by teachers | Display resources | N/A | September 2018 | By October 2018, displays regarding the Bronze award will be in place to show Meadowlane is a school in Wales that promotes bilingualism. |
| - Each week in assemblies, promote current target/ phrase, sing Welsh songs, Criw Cymraeg presentations. | LM | Assembly plan | N/A | Ongoing from September 2018 | By November 2018, children will be able to talk about the Welsh that is used within assemblies. By July 2019, most children will be joining in with Welsh songs with confidence. |
| - Each half term there will be a focus Welsh person for the school. | LM | Display | N/A | Ongoing from September 2018 | By February 2019, most children will have knowledge of at least three Welsh people who have helped shape our modern world. By July 2019, most children will have knowledge of at least six Welsh people who have helped shape our modern world. |
| - Use twitter/ website to make bilingual links with home. | LM supported by teachers, AO and ST | Twitter/ web accounts | N/A | Ongoing from September 2018 | By March 2019, many parents will have a good understanding of the importance of Welsh at Meadowlane. To show MLPS is a school in Wales that promotes bilingualism and encourages our parents to have a go at speaking Welsh. |
| - Parents to be provided with Welsh training courses. | AO | Supporting college? | N/A | To be confirmed | By July 2019 a group of parents will have attended the Welsh training course and will be supporting promoting Welsh to other parents at Meadowlane. |
| - Ensure CPD opportunities are planned for staff that require development in their Welsh language skills. | JR | CPD records | Covered by WAG | Ongoing as required | By July 2019, many staff will feel confident in using basic welsh language skills with the children. |
| MATHS Aim: - Ensure full coverage of the Maths Programme of Study - Ensure all teacher assessments are accurate |  |  |  |  |  |
| - Half termly Building blocks monitoring reports will be analysed to ensure coverage of concepts. | JM supported by teachers | Building Blocks | £954 PDG funded | Oct 18, dec 18, Feb 19, Apr 19, May 19, Jul 19 | By December 2018, gaps in Maths coverage will be identified and planned into the Spring and Summer terms. By April 2019, gaps in coverage will be identified and planned into the summer term. |
| - Maths wallpaper exercises will be undertaken termly to identify strengths and areas for improvement in aspects of writing/ marking/ moderation of levels. | JM | INSET | N/A | 3/9/18 Januray 2019 May 2019 | By September 2018, all teachers will understand areas that require improvement in maths and each Key Stage will have a plan to address these. By January 2019, the areas needing improvement from September 18 will have been addressed and further areas will be identified and planned for. To be repeated in May 2019. |
| - SLT to make relevant changes relating to expected outcomes/sublevels, adding further challenge in line with the new PoS | JM supported by SLT | SLT meetings | N/A | September 2018 | By September 2018, SLT will have shared the raised expectations for standards in Maths. By July 2019, 90% children will achieve Level; 4 and 40% will achieve Level 5. By July 2019, 90% children will achieve Outcome 5 and 40% children will achieve Outcome 6. |
| SCIENCE Aim: To ensure all teacher assessments are accurate |  |  |  |  |  |
| - Book scrutiny to be carried out to include a focus on marking and feedback and moderation of Science levels. | LW supported by RW | Supply cover | £135 – main supply budget | March 2019 July 2019 | By May 2019, cluster moderation will confirm the school’s teacher assessments as accurate. By July 2019, marking and feedback will be consistently good in all classes leading to good progress for most children. |
| - Science wall paper to be carried out, focusing on marking/feedback, continuity and progression, and moderation of levels. | LW | INSET | N/A | January 2019 | By January 2019, all teachers will understand areas that require improvement in Science and each Key Stage will have a plan to address these. By March 2019, the areas needing improvement will have been addressed. By May 2019, cluster moderation will confirm the school’s teacher assessments as accurate. |
| WHOLE SCHOOL Aims: - Ensure effective CPD to continue improving teaching and to support staff in working towards a new curriculum with a focus on the pedagogical principles - Ensure regular and effective communication with parents to support them in being involved in school life - Further develop middle leaders to enable them to monitor their areas of responsibility accurately and effectively |  |  |  |  |  |
| - Plan INSET sessions focusing on the use of effective questioning, using the Continua for Teaching to support. Teacher triads to take place with a focus on questioning. | RW supported by CF | INSETs Supply cover for triads | £1235 (13x0.5 days) PDG | 16/10/18 11/12/18 | By February 2019, lesson observations will highlight effective questioning that challenges children in nearly all classes. |
| - Plan INSET sessions to further develop effective feedback; written and oral. | RW | INSETs | N/A | 3/9/18 2/10/18 | By December 2018, book scrutiny will show marking is having a positive impact on pupil progress in nearly all classes. By July 2019, most children will have made good progress supported by the effective feedback they have received from staff. |
| - Continue work in Research teams to continue developing the pedagogical principles and the new curriculum. | JM | INSETs Supply | £1235 PDG | Spring 2019 | By April 2019, all teachers will have disseminated their learning from research with all staff. |
| - Follow the strategic monitoring plan to ensure a range of evidence is collected from pupil discussions, book scrutiny, drop ins, lesson observations, data and learning walks to evaluate school effectiveness accurately. | CF supported by the SLT | Supply cover for SLT | £1500 | Ongoing from September 2018 | By December 2018, all outcomes from monitoring activities will be fully evaluated and used to inform INSETs and training needs for Spring 2019. By April 2019, all outcomes from monitoring activities will be fully evaluated and used to inform INSETs and training needs for Summer 2019. By July 2019, all outcomes from monitoring activities will be fully evaluated and used to update the school’s self-evaluation report and write the SDP for 2019/2020. |
| - The skills and abilities of staff to be monitored through the strategic monitoring plan. Personalised CPD opportunities to be planned where required, observing excellent practice and whole staff INSET to be planned where required. | JR supported by the SLT |  | £12000 PDG |  | By July 2019, nearly all teaching will be good or better with a majority excellent. |
| - i-Voice group to attend lesson observation and learning walks and provide staff with feedback. | RW supported by CF | N/A | N/A | WB 1/10/18 WB 26/11/18 WB 28/1/19 WB 18/3/19 | By July 2019, very few children will speak about being actively involved in playing a full part in the life of the school; supporting improvements in teaching and the curriculum. |
| - Termly assembly plans to be written with weekly focus. | CF | N/A | N/A | September 2018, January 2019, April 2019 | By July 2019, a wide range of well-being aspects will have been covered through assemblies. Different people, including children, will have led assemblies. |
| - Continue to use Twitter, Schoop, newsletter and the school website to communicate effectively with parents. | CF supported by AO and ST | Schoop Website Twitter | £700 PDG £500 PDG | Ongoing from September 2018 | By July 2019, parent questionnaires will show most parents feel they are kept well informed about what is going on in school. |
| - Continue with NEET project working with school and education organisations from Finland, Sweden and Romania. | CF | Supply cover | Fully funded through the British Council | Ongoing from September 2018 | By November 2018, 5 pupils will have visited Romania to raise aspirations and experience school in another country. By July 2019, a group of parents and governors will be working together to identify reasons for NEET and how to address this. |
| - Middle Leaders to monitor their subject responsibilities using a range of strategies. | CF | Supply cover | £400 from main supply budget | Ongoing from September 2018 | By July 2019, all curriculum middle leaders will have produced a report for governors, using evaluations from their monitoring activities. |
| - Plan appropriate safeguarding training. | RW | INSETs | N/A | 3/9/18, 13/9/18 12/9/18 4/12/18 | By December 2018, all required safeguarding training will have been attended by nearly all staff. Further training will provided for any new staff. |
| Staff well-being Aim: Develop as a health promoting workplace, which demonstrates concern for the wellbeing of all staff |  |  |  |  |  |
| - Introduce Well-being Wednesday for staff. | RW with support of all staff. | Back massagers | £200 | Spring 2019 – Ongoing | By January 2019, all staff will have access to back massagers in the staff room during break times. By July 2019, nearly all staff will report the school is a health promoting workplace, which demonstrates concern for the wellbeing of all staff. |
| - Plan Team building INSETs to support staff well being. | CF | INSET | £500 PDG | 29/4/19 | By July 2019, nearly all staff will report the school is a health promoting workplace, which demonstrates concern for the wellbeing of all staff. |
| - Staff member to take responsibility for Staff Well-being and to organise half termly Circle Time for staff. | CF | INSETs and Tuesday meetings | N/A | Half termly from October 2018 | By July 2019, nearly all staff will report the school is a health promoting workplace, which demonstrates concern for the wellbeing of all staff. |
| GOVERNORS - To enable all governors to challenge the school effectively through an increased understanding about the school’s strengths and areas for improvement. |  |  |  |  |  |
| - Termly governors weeks | CoG | N/A | N/A | WB 1/10/18 WB 26/11/18 WB 28/1/19 WB 18/3/19 | By December 2018, nearly all governors will be confident to challenge and support the school effectively. |