| KEY PRIORITY 3: School’s as Learning Organisations Goal: All stakeholders are invested in their own Professional Learning Journey; understanding the new curriculum, keeping up with current outstanding practice- so all our learners are challenged and making good progress. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Success Criteria: - Nearly all stakeholders are invested in their continued professional learning journey. - Most children are making good progress due to the support and challenge they receive - Most staff are taking part in research, trial, reflection and evaluation, supported through professional dialogue. |  |  |  |  |  | Autumn; Spring; Summer. |
| Leaders: Jayne Rogers |  |  |  |  |  |  |  |
| Actions | Personnel Involved | Budget / Resources (Human, time and physical) | Timescales | Self Evaluation Activities | Self-Evaluation |  | Evidence |
| 1.Use the ‘Hwb Legacy SLO Survey’ to inform professional learning opportunities for all stakeholders. | JR | N/A | By September 21 | SLO survey evaluation |  |  |  |
| 2. Training opportunities will be responsive to the identified needs of all staff. | JR supported by SLT | SLT time | By Nov 21, Jan 22, Apr 22 plan for future Learning opportunities in place. | Evaluate Professional Learning opportunities against ‘Future Learning’ plan. Evaluate learning opportunities against Hwb Legacy survey. Evaluate learning opportunities from Performance Management Reviews CPD evaluations to show impact of Professional learning |  |  |  |
| 3.Provide training for all teaching staff on developments in Curriculum Design. Utilise opportunities from the CCS. | JM & JR supported by SLT and all teachers | INSETs 30/11, 7/12, 14/12 Internal Cover | By July 22 all teaching staff will have accessed PL on the new curriculum. | INSET Diary and minutes will reflect PL opportunities Lesson observations will highlight language of the new curriculum being used by all staff. Planning scrutiny will identify all aspects of the new curriculum. |  |  |  |
| 4. All Support Staff will access in house new curriculum design training. | JM & JR supported by SLT and TAs | INSET 3/9/21 | BY July 22 all support staff will have accessed PL on the new curriculum. | INSET Diary and minutes will reflect PL opportunities. Lesson observations will highlight language of the new curriculum being used by TAs. |  |  |  |
| 5.All governors to receive ongoing training on the new curriculum for Meadowlane. Governors to meet with their AoLE links to deepen understanding in their allocated areas. | CF, JM & JR Governors | INSET Time Governors meetings | By July 22 governors will have a good understanding of the new curriculum. | Governors meeting minutes |  |  |  |
| 6. Most parents will understand the vision Meadowlane has for the new curriculum and will have the opportunity to contribute to the curriculum design planning stage. | JR, JM | Internal cover | By December 21 all parents will have had the opportunity to contribute to Meadowlane’s curriculum design. By July 2022 most parents will have an understanding of Meadowlane’s vision for the new curriculum. | Twitter, Class Dojo Parent questionnaire |  |  |  |
| 7. All staff have opportunities to work in triads to research, trial then reflect upon an aspect of pedagogy. PL discussions will reflect a deeper understanding of research undertaken. . | Whole staff | Internal cover INSET Time | By December 21 all staff have an aspect of pedagogy to research. By Spring 22 all staff have time to implement strategies as a result of research taken. By Summer 22 all staff have time to reflect and share experiences/ impact on learning gained from triad work. | Triad presentations Lesson observations Listening to Learners |  |  |  |
| 8.Staff have opportunities to work within Cluster Groups to develop an aspect of their AoLE. Science and Technology: Cities of the Future Project Humantities: Our Locaility Project LLC: Developing the teaching of phonics M&N: Outdoor Maths Expressive Arts: Incorporating drama into each of the AoLEs Health and Well-being: Cluster Well being Wednesdays | All AoLE members across cluster | Internal cover Cluster INSET Day 28/2/22 All INSETs – Spring 2 | By July 21 all AoLE groups will arrange meetings to discuss aspects of area to develop. By October 21 all staff will have time to research/ gather ideas to develop their aspect of their AoLE By November 21 all AoLE cluster groups will have time to trial the impact upon learning of aspect being developed. By February 22 all AoLE cluster groups will feedback on impact on learning of aspect of new curriculum researched to Cluster Leader. | Learning Presentations Cluster website Twitter, Class Dojo Listening to learners |  |  |  |
| 9.Cluster staff INSET Day to have professional discussions about learning experiences/ environments/ research/ linked to new curriculum. | Whole staff | INSET Day 28/2/22 | Feb 28 Cluster Inset day | INSET Evaluations |  |  |  |
| 10. Staff have opportunities to work in SIG groups to develop further understanding of aspects of pedagogy | RW SIG group TBA | Internal cover | By Summer 22 SIG group have worked together to further understand an aspect of the new curriculum pedagogy- how implementation impacted learning. | SIG learning presentations Listening to learners Lesson Observations |  |  |  |
| 11.PL opportunities are identified through Performance Management discussions. | PM leaders/ teams | Internal Cover | By October21 | INSET plan CPD records and evaluations |  |  |  |
| 12. Through PM all staff have opportunity to develop an area of interest to research, trial, evaluate impact on learning- through ‘Passion project.’ | PM leaders All staff | Internal cover | By Oct 21 all staff will have opportunity to share interest in PMT- passion project. By May 22 all staff will have opportunity to research, trial ‘Passion Project.’ By Oct 22 all staff will reflect upon impact on learning from PP work. | PM reviews Passion Project learning presentations |  |  |  |
| 13. SLT to discuss any required training needs on a regular basis and plan how to meet these needs. | JR and SLT | SLT meetings INSETs: 2/9 Yasmine PE training 3/9 Professional Behaviours Fortnightly during Autumn Term – Welsh Games 28/9 School Development Plan 12/10 Chrome Book training 19/10 Voice 21 training | By July 2022 most staff feel confident in supporting and challenging the children in all aspects of school life. By July 2022 nearly all staff feel their professional development needs are met. | INSET minutes Listening to learners Lesson Observations Learning Walks Pupil progress Meetings |  |  |  |
| 14. Governors to ensure all required training is attended and completed. Governors invited to attend INSETs. | CF and DM-W Governors | Governors meetings INSETs | By July 2022 governors will have a good understanding of all aspects of school life. | Governors meeting minutes |  |  |  |