| KEY PRIORITY – Relationships Article 18 – Parental responsibilities Article 28 – Right to Education Article 29 – Goals of Education Goal: To continue to develop positive relationships throughout the school community. Rationale: At Meadowlane, fostering positive working relationships with the wider school community remains a key priority. By cultivating these supportive and nurturing connections, we aim to ensure that the well-being needs of all children are effectively met to enhance children's readiness to learn and to support great progress. We are committed to strengthening our partnerships with parents to promote regular attendance by bridging the home school gap. We remain committed to engaging with community organisations to establish a comprehensive range of services designed to support the children and their families at Meadowlane. In 25/26, we plan to further strengthen relationships between children, with a focus on positive play, to reduce the negative behaviours observed. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Success Criteria: - Yearly attendance increases from 88.6% because of increased parental engagement throughout the school year. - Exclusions will decrease from 40 due to positive play opportunities. - Community engagement effectively supports the well-being of nearly all children, evidenced through the Whole School Approach to Mental and Emotional Well-being questionnaire that will show progress from 2024. |  |  |  |  |  | Autumn; Spring; Summer. |
| Leaders: Tom Simmonds |  |  |  |  |  |  |  |
| Actions | Personnel Involved | Budget / Resources (Human, time and physical) | Timescales | Self Evaluation Activities | Self-Evaluation |  | Evidence |
| CHILDREN & STAFF |  |  |  |  |  |  |  |
| 1. All staff to continue using nurturing language; reminders to be given through briefing and staff training sessions Nurturing language presentation to be shared with the staff at INSET in September | All staff | Staff Meetings INSET – September 2025 | From September 2025 then on going throughout the year | Pupil discussions Learning walk New staff to meet with TS for nurturing language introduction Inset diary |  |  |  |
| 2. Children and staff to be reminded of high expectations for manners and polite behaviour. Pupils and staff to encourage each other to use good manners. Focus on: - Saying please and thank you - Holding doors for each other - Walking through corridors and down stairs - Using Welsh | TS All Staff | September 2025 INSET Whole school assembly | 1/9/25 Throughout the year | Pupil discussions Learning Walks |  |  |  |
| 3.All staff to continue to use whole class strategies to help build positive relationships in class. Teacher’s will complete: - A weekly circle - A daily greeting - A daily check in (Sut wyt ti?) on class dojo - Use digital developmental profile data to address class and individual needs | All staff | September 2025 INSET Reminders throughout the year in INSETs and meetings | From September 2025 then ongoing throughout the year | Pupil discussions Learning Walks |  |  |  |
| 4. A second weekly review circle to be introduced for teachers and their classes to complete at the end of the week. The circle will be a chance for pupils to celebrate their achievements and give a forum for pupils to apologise. | TS All staff | September 2025 | From September 2025 then ongoing throughout the year. | Pupil discussions Learning Walks |  |  |  |
| 5. Nurture International profiles completed twice a year to track and identify barriers to learning and common trends. Teachers to implement strategies in class to address barriers. For example, self regulation. Dosbarth Monnow specialist provision classroom to support identified pupils in meeting their individual needs. Article 28 – Right to an education. | Teachers | £1000 PDG | January and July | Digital Developmental Portrait Data Learning walks Pupil discussions Individual targets |  |  |  |
| 6. All staff to continue to use whole class strategies to help build positive relationships in class Restorative behaviour steps and approaches to be followed consistently by all staff Restorative approaches presentation to be shared with staff in September INSET Teacher’s and support staff to have strong classroom routines to ensure a consistent approach across the school. New day, new beginning Supply teachers issued with the restorative steps to follow | Teachers | N/A | Ongoing throughout the year | Pupil discussions Behaviour records – Provision Maps Weekly Circles planning |  |  |  |
| 7. Staggered play times to allow children to play with more space to continue. Children to be encouraged to play a range of different games at play time. Behaviour, manners and expectations to be modelled by all staff. | All Staff | Playground resources - £500 | From September 2025 | Learning walks |  |  |  |
| 8. Participation in the Education Catalyst Pilot Programme led by the Youth Endowment Fund. EPIC self assessment tool to be completed Work with a Catalyst Partner to co-develop a Theory of Change. Share learning and contribute to national evaluation and policy development. | TS/ CF | Funded by the Local Authority | Date to be confirmed | Exclusion numbers Provision Maps records |  |  |  |
| PARENTS |  |  |  |  |  |  |  |
| 8. Share timings of the day with parents through Class dojo, website and newsletters. | AO | Dojo school website | First week of every half term | Percentage of ‘lates’ analysed |  |  |  |
| 9. Rewarding Attendance Weekly class attendance announced in assembly – trophy and reward (extra play) Half termly 100% attendance reward - classes – non uniform day Half termly reward for parents with 100% attendance £50 voucher End of year Attendance trip | Admin TS SLT | PDG Rotary Club | Half termly | 100% attendance reports Pupil discussions I Voice |  |  |  |
| 10. Monitoring Attendance Fortnightly meetings with Attendance officer to identify support required Parental meetings with persistent absentees with deputy head teacher and attendance officer and a period of monitoring SLT to invite parents into school for attendance meeting followed by house visit if parent doesn't attend attendance meeting. Referral to EWS if required due to lack of engagement from parents Admin to phone home to carers of absent children before 10am and class teachers to check dojo for messages – if teacher messages parent they must inform front office. To include Nursery and Reception pupils. | TS Admin |  | Fortnightly | SIMs records Meeting minutes My Concern Provision Maps |  |  |  |
| 11. Listen to learners about their views on attendance and punctuality. I Voice | I Voice SLT | I voice | Half termly | I voice minutes |  |  |  |
| 12. Collect baseline data on attendance and punctuality in school for CLIP | TS |  | Autumn term | Baseline data |  |  |  |
| 13. Ensure all vulnerable groups are identified correctly on SIMs (CP, CASP etc) | Office manager TS |  | Weekly | SIMs data |  |  |  |
| 14. Implement CLIP actions to improve attendance. | TS SLT |  | Weekly | CLIP interventions and actions – minutes |  |  |  |
| 15. Parents evenings offered 3 times during an academic year – during the first parents evening expectations set out by the teacher; leaflets shared with facts of missed hours. | Teachers Admin officer | INSET time to agree expectations to share Directed Hours | Autumn Spring Summer term | Records of parents who did not attend logged onto provision maps and parent contacted |  |  |  |
| 16. Share topic placemat with parents in reference to the classes learning journey. | Teachers | PPA | At the end of each topic | Placemats - dojo and website. Placemats saved in All Staff Team, Learning Reviews Channel |  |  |  |
| 17. Parents invited into school at least twice a term to either work with their child or to attend information sharing sessions. Open afternoon – Parents invited to learn about what the Meadowlane curriculum. | TS SLT | Open afternoon H&W morning Spring Term events Summer Term events | 30/9/25 10/2/26 19/9/25 | Invites Dojo |  |  |  |
| COMMUNITY |  |  |  |  |  |  |  |
| 18. Meadowlane to develop working relationships and partnerships with the local community. Community focussed school’s officer Laura Croft and family engagement officer (to be appointed) to support. | All staff Laura Croft Family Engagement officer |  | From September 2025 | Class Dojo |  |  |  |
| WHOLE SCHOOL |  |  |  |  |  |  |  |
| 19. Whole School community to complete the WSAMEW questionnaire. -Pupils -Parents/Carers -Teachers -Governors Results will be used to update, the WSAEMW self-evaluation tool. TS to share the schools WSAEMW journey with other schools with Karen Trigg | TS with support of all staff |  | By December 2025 | WSAEMW questionnaire results |  |  |  |
| 20. I-Voice to evaluate the effectiveness of this plan during the year and at the end of year self-evaluation day. I-Voice will also be involved in self-evaluation days. | Chloe Ford | I-Voice day at The Hive (£50 PDG) | 26/6/26 | I-Voice Evaluation |  |  |  |